## BD18-12345
NCR - 0 to 15 days
NCR - 16 to 44 days
NCR - 45 days and up
Work covered or loaded
ROC Issued
[5 empty] | Clark County Building Department 4701 W. Russell Road • Las Vegas, NV 89118 (702) 455-3000 • Fax (702) 221-0630 Jerome A. Stueve, P.E., Director Samuel D. Palmer, P.E., Assistant Director • James Gerren, P.E., Assistant Director |  |  |  | Agency Logo
[9 empty] | Start-Up Form Date: |  | 2021-02-02
Project Name: |  |  |  |  | Naaltsoos Sání Casino & Resort |  |  |  | Today's Date: | 2021-12-21
[9 empty] | BDIA Number: | BDIA19-00012
Form 887 Inspection Agency Name: |  |  |  |  | Gur Consulting & Inpections Inc. |  |  |  | Permit Number: | BD18-12345
| Work Covered or Loaded? | SEOR Approved? | CCBD Approved? | NCR number | NCR Scope - Gridline / Elevation Location | Date of Issuance | ROC Date | No. Days from NCR Issuance | RFI number / Revision No. / Comments
FALSE |  |  |  | NCR-CR-01 | Wrong longitudinal rebar size at shear No.8 instead of No. 9, located at C.25 from 3 to 6.5, second level mezzanine | 2021-12-15 |  | 6 | Non approved detail onsite RFI 0032 |  |  | FALSE | TRUE | 2018-01-01 | FALSE | FALSE | 1
FALSE |  |  |  | NCR-CC-02 | Not approved mix design for shear wall pour, located at C.25 from 3 to 6.5, second level mezzanine | 2021-11-20 |  | 31 | GC mentioned that CC requested corrections, missing PE stamp |  |  | FALSE | TRUE | 2018-01-01 | FALSE | FALSE | 2
TRUE |  |  |  | NCR-SS-01 | A325 bolts for shear connection at A.5/C were left outside bolt container during two days prior to installation | 2021-09-20 |  | 92 |  |  |  | FALSE | TRUE | 2018-01-01 | FALSE | FALSE | 3
FALSE |  |  |  | NCR-CC-03 | Not approved mix design for concrete deck, existing NCR on connection beneath (See NCR-SS-010 | 2021-09-15 |  | 97 |  |  |  | FALSE | TRUE | 2018-01-01 | FALSE | TRUE | 4
FALSE |  |  |  | NCR-M-01 | Concesion buiding NEC, Not approved masonry inspector fabrication prisms on site | 2021-04-10 | 2021-12-15 | 255 | Agency mentioned that request has been submitted to CC |  |  | TRUE | TRUE | 2018-01-01 | FALSE | TRUE | 5
FALSE |  |  |  | NCR-M-02 | Not approved plans for consecion building at NEC | 2021-06-25 |  | 179 | GC mentioned that they are waiting for revision approval, non approved plans on site |  |  | FALSE | TRUE | 2018-01-01 | FALSE | FALSE | 6
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 7
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 8
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 9
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 10
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 11
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 12
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 13
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 14
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 15
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 16
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 17
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 18
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 19
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 20
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 21
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 22
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 23
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 24
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 25
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 26
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 27
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 28
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 29
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 30
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 31
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 32
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 33
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 34
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 35
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 36
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 37
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 38
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 39
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 40
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 41
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 42
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 43
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 44
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 45
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 46
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 47
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 48
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 49
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 50
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 51
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 52
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 53
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 54
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 55
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 56
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 57
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 58
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 59
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 60
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 61
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 62
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 63
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 64
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 65
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 66
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 67
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 68
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 69
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 70
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 71
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 72
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 73
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 74
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 75
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 76
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 77
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 78
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 79
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 80
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 81
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 82
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 83
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 84
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 85
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 86
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 87
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 88
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 89
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 90
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 91
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 92
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 93
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 94
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 95
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 96
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 97
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 98
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 99
FALSE | [7 empty] | 0 |  |  |  | FALSE | FALSE | 2018-01-01 | FALSE | FALSE | 100
FALSE
Formulas:
No. Days from NCR Issuance = IF([Date of Issuance]="","0",([Date of Issuance]-TODAY())*(-1))